## Gantchart
GST SMART MANAGER MONTHLY TASK GANTT CHART
PROJECT TITLE: GST SMART MANAGER | [6 empty] | INSTUTUTE & DEPARTMENT NAME: | [11 empty] | AP SHAH INSTITUTE OF TECHNOLOGY(CSE-Data Science)
PROJECT GUIDE: Prof Kiran Gaikwad
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION(Weeks) | PERCENTAGE OF TASK COMPLETE | PHASE ONE | [34 empty] | PHASE TWO
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[7 empty] | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F
1 | Project Conception and Initiation
1.1 | Project setup & system architecture | A,B,C,D | 2026-01-10 | 2026-01-16 | 1 | 100% | bar: WEEK 1 M to WEEK 2 T
1.2 | Firebase configuration & database design | A,B,C,D | 2026-01-17 | 2026-01-23 | 1 | 100% | bar: WEEK 2 W to WEEK 3 T
1.3 | Authentication & user profile setup | A,B,C,D | 2026-01-24 | 2026-01-30 | 1 | 100% | bar: WEEK 3 F to WEEK 5 M
1.4 | Profile enhancement | A,B,C,D | 2026-01-31 | 2026-02-06 | 1 | 100% | bar: WEEK 5 T to WEEK 6 W
1.5 | Presentation I | A,B,C,D | 2026-02-07 | 2026-02-10 | 1 | 100% | bar: WEEK 6 T to WEEK 7 T
2 | Project Design and Implementation
2.1 | Business setup & profile management | A,B,C,D | 2026-02-11 | 2026-02-17 | 1 | 100% | bar: WEEK 7 W to WEEK 8 T
2.2 | Client management & invoice tracking | A,B,C,D | 2026-02-18 | 2026-02-24 | 1 | 100% | bar: WEEK 8 F to WEEK 10 M
2.3 | Invoice generating & GST calculation | A,B,C,D | 2026-02-25 | 2026-03-05 | 1 | 100% | bar: WEEK 10 T to WEEK 11 F
2.5 | Security implementation & performance optimization | A,B,C,D | 2026-03-01 | 2026-03-05 | 1 | 100% | bar: WEEK 11 M to WEEK 11 F
2.6 | Testing & bug fixing | A,B,C,D | 2026-03-16 | 2026-03-25 | 1 | 100% | bar: WEEK 11 F to WEEK 12 M
2.7 | Documentation | A,B,C,D | 2026-03-26 | 2026-03-05 | 1 | 100% | bar: WEEK 12 M to WEEK 12 T
2.8 | Presentation II | A,B,C,D | 2026-04-06 | 2026-04-10 | 1 | 100% | bar: WEEK 12 F